## Project Report
Spring Into Action 2020
Project Report
Monday, February 17, 2020
SiteName | Active | Project# | OriginalRequest | ProjectDescription | Comments | BudgetSources | VolunteersAssigned | HasAttachments | Status | Status Reason | Primary Skill Needed | Location | Dimensions | Material Needed and Cost | Estimated Total Cost | Special Instructions | Team Leaders Needed Estimate | Volunteers Needed Estimate | Estimated time to complete the project? | Will this project be completed before or during Spring into Action? | Prep Work Required | Is a permit required for this project? (Please see the SIA Manual regarding permits) | What is the permit required for? | Would you like a member of the lead team to contact you regarding this project? | Is any special equipment needed for the project? | Wall Dimensions (Square feet est.) | Estimated Number of Paint Cans needed | Estimated rolls of painters tape needed | Paint already on hand | Paint ordered | Needs To Be Started Early | Actual Cost | Child Friendly | PC See Before SIA | Setup Day Instructions | SIA Day Instructions | Need SIA TShirts For PC | Project Send | Cost Estimate Done | Material List Done | Volunteer Allocation Done | Permits Or Approvals Done | Permits Or Approvals Status | Budget Allocation Done | Final Completion Assessment | Final Completion Status | PeopleNeeded
All Schools | 1 | 2 | TEST: We would like a shed to be built. A nice one. | 4454 | NOTE TEST. Additional 3 sheets 3/4" x 4' x 8' Oak veneer plywood 3 sheets ¾” x 4’ x 8’ Oak veneer plywood | Woodlands | 0 | Yes | Approved |  | Landscaping/Furniture Making / Woodworking | The location is outside the school, near parking lot B. | Here are some dimensions. | 3 sheets 3/4" x 4' x 8' Oak veneer plywood:$35, Test:$3.00, Test:$20, Test:$6, Test:$19, Test:$45, Another Test:$15, 3 sheets ¾” x 4’ x 8’ Oak veneer plywood:$, 3 sheets 3/4" x 4' x 8' Oak veneer plywood:$ | 143 | Here are some special instructions | 2 | 25 | 4 hours | During | N/A | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Sent | Yes | No | Yes | No | Needs to be submitted | Yes |  | No | 20
All Schools | 1 | 3 | This is a test. | 3215 |  |  | 0 | No | Approved |  | General |  |  |  | 0 |  | 0 | 0 |  | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
Bannach Elementary School | 1 | 1 | general clean-up of grounds outside Jessica Champion | Clean-up grounds outside of Bannach | General picking up of garbage around Bannach school. looked at the job with snow on the ground. was hard to see just how much garbage was on the ground. But this is a routine job done each year. I would think that there is plans for this job from previous years? | Unknown | 0 | Yes | Approved |  | General/Cleaning | area outside of Bannach school |  | chips:$5 | 5 | Nothing special. just need junk picked up and put in the garbage. maybe need a wheel barrow or a little red flyer wagon to put the garbage in while walking around? | 1 | 4 | 2-3 hours? | During | N/A. show up and do the job and go home | No |  | No | [6 empty] | Yes | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 4
Bannach Elementary School | 1 | 2 | clean-up flower beds in the front of the building to include planting flowers front of the building Jessica Champion | Cleaning and planting flowers at Bannach's main entrance | Cleaning out the planter boxes at the main entrance of Bannach school and planting new flowers in them. This also is a job that is done yearly and I think there is information on this from previous years | PTO | 0 | No | Approved |  | Landscaping/General/Cleaning | Main entrance south side of schol |  |  | 0 | The flowers will be provided by the PTO. will need gardening tools | 1 | 4 | 3-4 hours | During | N/A. show up the day of. | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 4
Bannach Elementary School | 1 | 3 | apply new layer of wood chips on playgrounds playground space Jessica Champion | Put woodchips on the Bannach playground | Need woodchips put on the Bannach playground. This should be a yearly project as well. | School | 0 | No | Approved |  | Landscaping/General | Playground west of school |  |  | 0 | Would probably be good to have a utility tractor around to help spread the woodchips and also for Job #4. But I am not sure what they did in previous years for spreading the woodchips. | 1 | 5 | 4 hours | During | N/A | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 4
Bannach Elementary School | 1 | 4 | enhance the berms around the outdoor classroom space (additional dirt - private donation), landscape fabric (private donation), plants, tree (purchased by the school account), flowers (donated by memorial garden committee) southeast end of grounds Jessica Champion | Build up berms for a memorial garden South of Bannach school | Need people to build up berms for a memorial garden outside of Bannach school. That is all that needs to be done is to add dirt( which will be from a private donation) to the berms to build them up. Jessica will know exactly how tall she wants them when springtime rolls around | School | 0 | No | Approved |  | Landscaping/General | South/ Southwest of the school | 2 berms roughly 50'x25' Will know clearer dimensions in spring time |  | 0 | Would be nice if there was a utility tractor to use. this would also cut down on the manpower needed and could be use to spread the woodchips on the playground | 1 | 8 | 3 hours | During | N/A | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 7
Ben Franklin Junior High | 1 | 1 | Paint room 2018. 2018 Brooke Walsh, Jeff Tepp |  | White south boards on wall painted ice cube North, East and West walls paint with ICELANDIC | Unknown | 0 | No | Pending |  | Painting/General | Rm 2018 |  | Ice Cube paint on south wall 2 Gallons:$, Ice- landic color 3 Gallons:$ | 0 |  | 0 | 0 |  | During |  | No |  | No |  | 1200 |  |  |  |  | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
Ben Franklin Junior High | 1 | 2 | Please refresh the wood chips on the Ben Franklin Forest trails Ben Franklin Forest, by BLISS center Carrie Vrieze/Cindy Solinksy/Science Dept | refresh the wood chips on ben franklin forest trials, need more woodchips than used last year. | had a hard time getting wood-chips in the past. Check old spread sheet for possible bark numbers | Unknown | 0 | No | Approved |  | Landscaping | School Trail |  | need wood chips, more than last year:$ | 0 | West of the Buss center on the path skid steer would work great for spreading wood chips, with about 4 volunteers leveling it off. | 1 | 4 | 3-5 hours | During | maybe get woodchips on site before hand. | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 4
Ben Franklin Junior High | 1 | 3 | 1012 could use a fresh coat of paint after holes are filled as well. 1012 Julie Raschka and/or Kim Falduto | Paint room 1012 | Paint all walls agreeable grey color | Unknown | 0 | No | Approved |  | Painting | Room 1012 | 14' X 15' | Paint agreeable Grey color 3 gallons:$ | 0 |  | 1 | 2 | 3 Hours | During |  | No |  | No |  |  |  |  | no |  | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 2
Ben Franklin Junior High | 1 | 4 | Office to be painted in Main Office. Main Office Tabitha Prutz or Kim Falduto | Paint room 1005c | Have to find out if all walls get painted because there is some paneling on wall. Do not paint west wall with tv on it Paint other 3 walls agreeable grey paint wood trim on south wall white The tack board may need to be primed first | Unknown | 0 | No | Approved |  | General | 1005C | 9' X 15' | Agreeable grey _____ Gallons:$, White _____gallons:$ | 0 | Have to find out if all walls get painted because there is some paneling on wall. Do not paint west wall with tv on it Paint other 3 walls agreeable grey paint wood trim on south wall white The tack board may need to be primed first | 1 | 2 | 3 hours | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 2
Ben Franklin Junior High | 1 | 5 | Roofs for the BF baseball and softball dugouts (we looked at this last year but were unable to weld onto the existing supports) Baseball & Softball Fields Dan Gagnon |  | Here are some additional notes. | Unknown | 0 | No | Approved |  | General | baseball field |  |  | 0 | Will Need Permit | 0 | 0 |  | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
Ben Franklin Junior High | 1 | 6 | Baseball Backstop Extension Net - Add an extension that comes out above the existing backstop to prevent foul balls from landing on the Bliss Center roof. Ben Franklin Baseball field Dan Gagnon / coach Tim Merrill |  | Here are some additional notes. | Unknown | 0 | No | Approved |  | General | baseball field |  |  | 0 |  | 0 | 0 |  | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
Boston School Forest | 1 | 1 | Our major project this year will be clearing brush and repairing trails damaged in the July 20th storm. A chipper, tractor with grapple, and skilled laborers are needed for a part of it (John Theime and his crew have been AMAZING in the past years). We may also request that John help us to remove some high-risk trees. We will need a crew on Sunday to help us rake wood chips and trim back trails. We would also like to redo a trail near the pond that will take some 4x4 posts for retaining soil. Grounds Karla Lockman & Sandy Masterson | Raking/Spreading Mulch, Stacking brush, repairing in-ground stairs | Spread mulch in High Ropes and Archery areas, stack brush along trails for chipping, and re-make and in-ground stairway next to the pond | School | 0 | No | Approved |  | Landscaping/General | Boston School Forest |  | no materials needed:$ | 0 | Mulch will need to be placed in the High Ropes and Archery areas. Brush will need to be gathered from the woods and stacked along the Sandman Shortcut trail and Shady Spruce trail for the chipper truck. Old stair timbers will need to be replaced near the Pond. | 3 | 15 | 3-4 hours | During | none | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 12
Boston School Forest | 1 | 2 | We may also request that John help us to remove some high-risk trees. We will need a crew on Sunday to help us rake wood chips and trim back trails. |  |  |  | 0 | No | Approved |  | General |  |  |  | 0 |  | 0 | 0 |  | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
Boston School Forest | 1 | 3 | We would also like to redo a trail near the pond that will take some 4x4 posts for retaining soil. |  |  |  | 0 | No | Approved |  | General |  |  |  | 0 |  | 0 | 0 |  | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
Fernandez Center | 1 | 1 | For the 2020 Spring into Action project, we would like to have the wallpaper removed on the wall between the office and conference room doors in the hallway on 1st floor. In addition, have that wall painted and have all of the class pictures re-positioned to include recent years. Currently we end with Class of 2015. I would also like to remove the names from the photos (for confidentiality). We could put them behind the photo but this way the names are not showing on the front. We already have the picture frames. Hall way on 1st floor Jennifer Knecht, Principal | Paint wall and place modified pictures/ | Here are some additional notes. | Unknown | 0 | No | Approved |  | Painting/General |  |  |  | 0 | We have paint left from previous projects. | 0 | 2 | 5 hours | During | Project 2 will strip wallpaper and prep for painting. Saturday before SIA. | No |  | No |  |  |  | 1 | 3 gallons |  | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 2
Fernandez Center | 1 | 2 | Remove wallpaper is a separate project to be done on Saturday. See the main project description Jennifer Knecht | PREP: strip wallpaper and re-frame pictures | Here are some additional notes. | Unknown | 0 | No | Approved |  | General |  |  |  | 0 |  | 0 | 2 | 3 hrs | Before | none | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 2
Jefferson Elementary School | 1 | 1 | Ball Bin for front of school Door 2 Stacy Janssen | This is a small outdoor "shed" for storing a single garbage can that is used to hold balls and other playground equipment. | Scott Edwards as potential team leader. Scott constructed one of these last year and the Jefferson folks are so happy with it that they are asking for another one exactly like it. I do not know how much it cost Scott to make the one from last year. He delivered it the day of SIA. | Unknown | 0 | No | Approved |  | General Carpentry/General |  |  |  | 0 | Scott would know... | 0 | 0 |  | Before |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
Jefferson Elementary School | 1 | 2 | Proposed Project List with Brief Description Special projects: In the garden area along Oak and East New raised beds-current wood is rotting Cheap and Easy Raised Bed Gardens Construct compost bins behind red shed-pallets Pallett Compost Bins Adjust the door on the red shed-it has shifted down so that it does not close properly Paint the shed & trim on the red shed Annual projects: Around the school building-N, E, S, W sides if time Clean debris (dead plant growth, dead leaves, litter) around the school building and in any plant area Across the “street” in front of school Fill wheelbarrows with mulch, dump and spread/rake wood chips in the outside classroom. Do the same under the swings along Jefferson St. and under the swings on the north side of the playground-along Oak St.-unless Buildings & Grounds does this later in the summer Depending on Stage re-construction, pull weeds around the stage, possibly spread mulch between the plants Depending on upcoming construction-The Quiet Area in back of school Adjust the edging around the brick low sitting wall & around the bed next to the building beside the dumpster-it’s been challenging to get the edging down far enough over the last couple years and it keeps rising up again-possibly just pull the edging that is sticking up & a trip hazard Spread mulch around the back quiet area Pull weeds around the building-if you see a weed, pull a weed :) *Ask Custodian: Where should yard waste be piled for pick up from Buildings & Grounds? Outside-see the Project list descriptions Not just one person | This is primarily a landscaping project to freshen bark and mulch around the school grounds. | No team leader needed as Project Manager can handle | School | 0 | No | Approved |  | General | Periphery of the school |  | bark/mulch:$ | 0 |  | 0 | 10 | 3-4 hours | During | none | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 8
Jefferson Elementary School | 1 | 3 | repaint the lost and found shelving unit and cubbie | repaint lost and found cubbie |  |  | 0 | No | Approved |  | Painting | in the foyer of the school |  | jefferson blue paint:$ | 0 |  | 0 | 0 | a few hours during SIA Sunday | During | none needed | No |  | No |  |  | 2 |  | none |  | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
Jefferson Elementary School | 1 | 4 | Paint the teacher workroom | paint the teacher workroom |  |  | 0 | No | Approved |  | Painting | Jefferson teacher workroom |  |  | 0 |  | 1 | 2 | 2-3 hours | During | none | No |  | No |  |  | 2 | 3 | yes-Jefferson to obtain paint. |  | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 2
Jefferson Elementary School | 1 | 5 | purchase a "sensory table" and a cubbie bin ahead of time and have them put together on Sia Sunday. | purchase prefabricated cubbie bin and sensory table (2 things). |  |  | 0 | No | Approved |  | Furniture Making / Woodworking |  |  | Sensory table cost $120:$120.02, cubbie bin $200 on amazon:$ | 350 |  | 1 | 2 | 2 hours | During | purchase items so they are ready to go the day of SIA | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 2
Kennedy Elementary School | 1 | 1 | Pack up materials from the library. During the summer the library will be remodeled and all materials need to be boxed up. Library Site Contact: Rose Helm | Pack Up Library - box up books/materials | New addition will affect quiet area. * School needs to tell us how to label the boxes, where the packed boxes should go, and if the office in 125A should be packed up too. | School | 0 | Yes | Approved |  | General/Cleaning | Library Rm #125 |  | none:$ | 0 |  | 1 | 7 | 4 hrs | During | Be sure boxes are at the site. The district is supposed to be supplying these. | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 6
Kennedy Elementary School | 1 | 2 | Kennedy Elementary school is trying to get an outdoor classroom built. They have been fundraising and believe they will have the fund necessary for the project to be built in the spring. Attached is a copy of the pictures I was sent by Kelly Kerchefski. The concrete has been poured and there are pole forms in place as well. The structure will need to be constructed. This will be a large undertaking. Site Contact: Kelly Kerchefski | Construct Outdoor Classroom | Jeremy Jonas and Brian Przybylski and Grandma Elaine want to be involved in this project. They have been organizing much of the fund raising. Permit Needed!! | School | 0 | Yes | Approved |  | Construction/General | West side of the school grounds, just west of the playground fence (there is a concrete slab there already). |  |  | 0 |  | 1 | 5 |  | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 4
Kennedy Elementary School | 1 | 3 | Heather Houston (speech teacher) is requesting a step to use for her Smartboard so that younger/smaller students can reach it and use it more effectively. Several of these were made for Kennedy a couple of years ago. She does have a very small classroom, so perhaps it would need to be a little shorter lengthwise but she would like a similar one with the storage under the carpeted top. Speech Room near the library Heather Houston | Build a Smartboard Step | This step should follow the design of the previously constructed smartboard steps, however this one may need to be smaller. The smartboard is 56" long. The space to work with is 8' long. The smartboard step needs to be slightly longer than the smartboard itself. | Unknown | 0 | Yes | Approved |  | Furniture Making / Woodworking/General Carpentry |  |  |  | 0 | The one picture attached here shows the smartboard step that was built last year. The other photo is the actual smartboard where this step will go this year. | 1 | 2 |  | Before | The smartboard step should be build ahead of time, and day of the event the step should be brought to the site and put into place. | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 2
Kennedy Elementary School | 1 | 4 | Makenzie Panzer is requesting a bookshelf like the ones that were built the past 2 years for Kennedy. She has a bookshelf but it doesn't have all the shelves it should so it is not as useful as she would like. Would alternately be interested in having Woodlands help her get shelves for her current bookshelf. Makenzie Panzer's classroom (I believe room 111) Site Contact: Makenzie Panzer | Building Two Bookshelves | Adjustable shelves top to bottom. The shelves need to hold baskets that are 13.5"x 8". No vertical partisans are needed for function. If necessary for structural integrity, then keep the basket dimensions in mind when determining where to put the partisan. Dave Z. is willing to build these as the TL. He built these in the past. Request is for two bookshelves - same size | Unknown | 0 | Yes | Approved |  | Furniture Making / Woodworking/General Carpentry |  | 4' wide 3' tall 1' wide each |  | 250 |  | 1 | 2 |  | Before | Build shelves before SIA. Bring to site and put into place day of event. | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 2
Kennedy Elementary School | 1 | 5 | The school is requesting new trellises for the garden area in the front of the school. They are also requesting that we re-do the landscaping. We can design whatever we want. Any type of bushes, shrubs, flowers, climbing plants...are welcomed. Another group will be planting 6 small pots to place at the front of the landscaping. The close up picture shows slightly where the pots go. The picture shows the darker circles where the pots sat. Front of the building (near door 1) Site Contact: Kelly Kerchefski | 3 Garden Trellises and new landscaping (woodchips/plants) | Current trellises are 51"x 24". Space between windows is 39.5" - trellises need to fit between the windows. Full space is 35' long x 51" deep John Aron (from Aron's Event Barn) may have plants he'll donate. | Unknown | 0 | Yes | Approved |  | Landscaping/General Carpentry | Front of building by Door #1 |  | wood for trellises:$, woodchips:$, plants:$ | 0 | Team lead for trellises Team lead for landscaping | 2 | 4 | 4 | During | trellises could be built ahead of time. Plants should be purchased early too. | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 4
Kennedy Elementary School | 1 | 6 | Due to the construction at Kennedy happening next year the room where the paper is stored is being taken for other use. This means the paper needs to be moved to the Workroom. The request has been made to help build shelves into the existing cabinets in the workroom that will be able to support the paper. If this request is approved, Educational Assistants will work together on what specific needs there will be. Site Contacts: Heather Stevens/Kelly Kerchefski | Building Shelves in Existing Cabinet | The coat rack in the cabinet can be removed, the existing shelf should stay (it is at 26" from the top of shelf) | Unknown | 0 | Yes | Cancelled |  | General Carpentry/General | Rm 131 | Cabinet is 39 | shelving materials:$ | 0 |  | 1 | 2 | 4 | During | Shelves could be cut ahead of time. | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 2
Kennedy Elementary School | 1 | 7 | Possible help in organizing an existing shed or building a small shed nearby. There is a shed on the very northeast side of the property, just outside the playground fence. This is where bikes are being stored for a biking unit in gym class. Currently the building is not holding the bikes well. Jean L is requesting help in either organizing (possibly with some sort of hooks or racks) the current shed or possibly building a small shed for the bikes. Northeast corner of property Jean L/Leon Z |  | PMs were not aware of this additional project until seeing it here. Need to learn more details. | Unknown | 0 | No | Approved |  | General | northeast side of property |  |  | 0 |  | 0 | 0 |  | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
Madison Elementary School | 1 | 1 | Kindergarten kitchen set for a dramatic play area. 158 Lauri Sroda | same as room 156- Lelcey Neveln, March 1st could be ? |  | Unknown | 0 | Yes | Approved |  | General | Room 158 |  |  | 0 |  | 1 | 2 |  | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 2
Madison Elementary School | 1 | 2 | Paint my cupboards. Room 133 Mary Bohlman | Paint the cupboards in Room 133. |  | Unknown | 0 | Yes | Approved |  | Painting | Room 133 Marry bohlman | 15"-2 |  | 0 | 4 photos white or tan color, Get this approved by school district | 1 | 2 | 3 hours | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 2
Madison Elementary School | 1 | 3 | I have 2 long benches that need to be recovered. Room 170 Kelly C Caufield | 3 photos |  | Unknown | 0 | Yes | Approved |  | Furniture Making / Woodworking | Room 170 Kelly Caufield | 3"H X 14"W X 63"L | Olive Green upholstery:$ | 0 |  | 1 | 2 |  | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 2
Madison Elementary School | 1 | 4 | 3 shelved book shelves, paint the cupboards in my room, bench for reading corner Room 121 Amanda Bushman | Building Book Shelf for room 121 |  | Unknown | 0 | Yes | Approved |  | General | Room 121 Amanda Bushman | Book shelf= 9.5"D x 2'W X 3'H |  | 0 |  | 1 | 2 | 2 hours | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 2
Madison Elementary School | 1 | 5 | If we could have 4-6 more rolling book bins for the library, as Doug has made in the past, we would be very grateful . Our easy section is slowly transforming! LMC Cathy Schroeckenthaler | 4-6 rolling book bins for library |  | School | 0 | Yes | Approved |  | General | Library | 2'-D x 27"H X 49.5"L | 4 wheels:$, wood:$ | 0 | 1 photo | 1 | 2 | 4 hours | Before |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 2
Madison Elementary School | 1 | 6 | Would like a record board placed in the cafeteria on the wall. Similar to the one I built at Jefferson. Also would like a bigger shoe rack as the one I have is a little too small. GYM Michael Feltz | Record Board= Jefferson |  | Unknown | 0 | Yes | Approved |  | General | Gym | Same as Jefferson school |  | 0 |  | 1 | 2 |  | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 2
Madison Elementary School | 1 | 7 | Storage needed - would like a tall cupboard (like above counter cabinets in other rooms) Room 125 Lori Musack |  |  | Unknown | 0 | Yes | Approved |  | General |  |  |  | 0 |  | 0 | 0 |  | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
Madison Elementary School | 1 | 8 | Paint the cupboards in my room Room 121 Amanda Bushman | Painting the cupboards |  |  | 0 | No | Approved |  | Painting | Room 121 | bottom is 15'L X 28"H X 2'D, top= 15'L X30"H x 13"D large cupboard= 6'-8"H X 3'W X 2'D Small cupboard= 40"L X 28"H X2'D |  | 0 |  | 1 | 2 |  | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 2
Madison Elementary School | 1 | 9 | Bench for Reading corner Room 121 Amanda Bushman |  |  |  | 0 | No | Approved |  | General | 121 |  |  | 0 |  | 0 | 0 |  | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
Madison Elementary School | 1 | 10 | Shoe Rack as the one i have is a little too small GYM Michael Feltz | Building a shoe rack for GYM teacher Michael Feltz |  |  | 0 | No | Approved |  | Construction | GYM | 69"L X 45.5"H X 12" D Openings 7-3/4" X 5'-2" Connect is 5'-4"D X 25-3/8"H | wood:$ | 0 |  | 1 | 2 |  | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 2
McDill Elementary School | 1 | 1 | Outdoor interactive play and garden area. Outside the kindergarten doors. Heather Bolton |  |  | Unknown | 0 | No | Approved |  | General |  |  |  | 0 |  | 0 | 0 |  | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
McDill Elementary School | 1 | 2 | I have a SMART Board in my classroom and I would love to have a SMART Board Step made so my students are able to reach all areas of the SMART board. I know that Woodlands made several for McKinley last year, I would love the same design. Thank you for considering my project. 124 Koree Rohde |  |  | School | 0 | No | Approved |  | General |  |  |  | 0 |  | 0 | 0 |  | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
McDill Elementary School | 1 | 3 | Book shelves would be appreciated in both first grade rooms, our are drooping and beginning to break. 123 and 121 Renee Schanck and Katie Abundiz |  |  | Unknown | 0 | No | Approved |  | General |  |  |  | 0 |  | 0 | 0 |  | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
McKinley Center Elementary | 1 | 1 | A small, skinny shed built outside gym door (on the outside of building) to house 2 racks of folding chairs as well as a compartment with rolling bins for playground balls and equipment. outside-black top area by gym door Rachel Graves | Storage Shed | The school is in need of a place to store (4) racks of chairs and (3) 55 gallon barrels filled with playground balls/toys. Each rack is 5.5' long x 3' wide x 6.5' tall. The configuration desired is to have the shed wide enough to house the chair racks side by side (6') and long enough for (3) racks wheeled in end-to-end (16.5') and the 4th will be in the next row in the back. The additional space (11') will be used for the barrels. | Unknown | 0 | Yes | Cancelled | The status was listed as cancelled when I got into this document. I took the information anyway in the event this was in error. | Construction/General Carpentry/General | Southeast exit of the Gym next to the concrete landing. | 8' wide x 18' long x 8' tall (interior dimensions, excluding roof) | Lumber (floor, walls, roof, door. Includes sheathing)/Shingles/Facia, soffit, frieze, tar paper:$1311.82, Vinyl Siding- complete:$315.63, Hardware (door, straps, hangers) and Fasteners (nails/screws):$125.00, Misc. -3 boards missed on lumber estimate:$30 | 1782.45 | Shed is requested to be tight to the building and leave the outlet (which is 2' to the west of the concrete landing) exposed. A ramp with a minimal lip is requested to the concrete landing to simplify moving the chairs and barrels. Ms. Graves also requests a sloped roof to prevent balls from being stuck. A shed roof is the best alternative. With a gable roof, balls can get caught on the building side of the roof. Aesthetically it is only important to blend in with the building. | 1 | 4 | 6-8 hours | During | The floor and building-side wall can be constructed in advance. As could the doors. Both could either be completed on-site or transported in a large trailer in sections. | Unknown |  | No | Roofing/framing nailers. General carpentry tools (miter saw, hammers, cutoff saw, level, ladders, drills) | [5 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 4
McKinley Center Elementary | 1 | 2 | Paint games on the blacktop for students to use during recess. Playground blacktop Kris Zasada | Painting Games/Activities on Asphalt | Ms. Zasada has requested (3) activities be painted on the asphalt outside of the kindergarten wing (southwest corner of the building). | Unknown | 0 | Yes | Approved |  | Painting/General | Southwest corner of the school. | Varies (see attachments) | 21 cans of spray paint (4-red, 4-yellow, 4-green, 4-white, 4-orange, 1- purple):$147.00 | 147 | Teacher requests the Alphabet Snake just outside of the Kindergarten doors (see IMG 0021, the Mirror Me just above the existing US map (see IMG 0022), and the Footmaze next to existing 4-Square (see IMG 0023). | 1 | 5 | 3-4 hours | During | Create Stencils | No |  | No |  | n/a | 5 | 5 | unknown |  | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 4
P. J. Jacobs Junior High | 1 | 1 | Trim and weed exterior, Spread mulch (12 yards) | Exterior landscaping. We will complete rain or shine. Bark spreading, weeding, tree trimming and brush removal. Bring rakes,gloves and shovels. | Contact person is Kelly Jung 715 572 8293 Kelly Jung will bring a 4 wheeler and trailer. I have already ordered the bark for PJs I have a chainsaw and trimmer. Volunteers needs to bring landscaping tools. | Unknown | 0 | No | Approved |  | Landscaping | PJ Jacobs JHS | None to note--perimeter map and expectations to be explained to landscaping leader prior to SIA. We will walk the ground together and establish understanding of the execution of the plan. | None to note--all to be brought in my volunteers:$, Bark is ordered from the district:$ | 0 | The mulch will be placed on the blacktop by the district. The brush and tree trimmings will be placed next to it and I have arranged for the district to pick it up on Monday morning. | 1 | 20 | 4 hours max | During | The prep work will be completed by project manager Kelly Jung (list of detailed needs of the grounds for the leader. I will also meet with the leader before the weekend). | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 16
P. J. Jacobs Junior High | 1 | 2 | Paint room 314 | Paint a classroom. | This room will be taped on the Friday before SIA. The classroom will be prepped, paint delivered and all materials will be in the classroom. Volunteers should wear light clothes if warm as the air conditioning will not be on. All classroom materials will be down and furniture out of the way. Kelly Jung will provide a classroom map so volunteers can move the items in the room back for class Monday morning. Please bring ladders. |  | 0 | No | Approved |  | Painting | Room 314 | 655 feet total to be painted | Paint brushes 2 pack 3x9.00:$0, Roller frames standard 3x5.00:$, Paint rollers brushes standard 2x3.99:$, Roller frames 4 inches 2x3.99:$0, Paint Rollers 4 inch 2x2.99:$, Paint Trays 2x2.99:$, Paint Cups 4x1.99:$, Paint 3x60:$, This feature was not working----------------------------->:$ | 265.56 | Paint will be purchased by the district and delivered prior to SIA Sunday. PJs will use Sand dollar. | 1 | 6 | Within the SIA allotted time | During | No prep work required as have a taping team coming in prior to painting. Teaching staff/custodial staff/project manager will have everything ready--plug and play, well paint. | No |  | No |  | 655 |  |  | NONE |  | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 5
P. J. Jacobs Junior High | 1 | 3 | Paint front wall in 002 **Contact is Kelly Jung 715 572 8293 ***** Please combine this project with # 5 and # 9 as it is only painting one wall | Painting a classroom. All material and prep work will be done prior to your arrival. | This room will be taped on the Friday before SIA. The classroom will be prepped, paint delivered and all materials will be in the classroom. Volunteers should wear light clothes if warm as the air conditioning will not be on. All classroom materials will be down and furniture out of the way. Kelly Jung will provide a classroom map so volunteers can move the items in the room back for class Monday morning. Please bring a ladder. |  | 0 | No | Approved |  | Painting | PJ Jacobs | Total feet to be painted: 217 | Paint Brushes 2 pack 3x9.00:$, Roller Frames standard 3x5.00:$, Paint Roller Brushes standard 3x5.00:$, Roller Frames 4 inches 2x3.99:$, Paint Rollers 4 inches 2x3.99:$, Paint Trays 2x2.99:$, Paint Cups 4x1.99:$, Paint 2x60.00 Sandollar:$, This feature did not work--------------------------->:$ | 265.56 | Paint will be purchased by the district and delivered prior to SIA Sunday. PJs will use Sand dollar. | 1 | 4 | within SIA time frame | During | No prep work required as have a taping team coming in prior to painting. Teaching staff/custodial staff/project manager will have everything ready--plug and play, well paint. | No |  | No |  | 217 total feet |  |  | NONE |  | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 4
P. J. Jacobs Junior High | 1 | 4 | Paint Room 217 Contact person is Kelly Jung 715 572 8293 | Painting classroom at PJ Jacobs. There is no prep work as the classroom will be ready for painting when you arrive. | This room will be taped on the Friday before SIA. The classroom will be prepped, paint delivered and all materials will be in the classroom. Volunteers should wear light clothes if warm as the air conditioning will not be on. All classroom materials will be down and furniture out of the way. Kelly Jung will provide a classroom map so volunteers can move the items in the room back for class Monday morning. Please bring ladders |  | 0 | No | Approved |  | Painting | PJJacobs | 700 feet | Paint Brushes 2 pack 3x9.00:$, Roller Frames standard 3x5.00:$, Paint rollers brushes standard 3x5.00:$, Roller frames 4 inch 2x3.99:$, Paint Rollers 4 inch 2x3.99:$, Paint Trays 2x2.99:$, Paint Cups 4x1.99:$, Paint 2x60:$ | 205.56 | Paint is ordered and will be placed in classroom. We are ordering sanddollar | 1 | 6 | within SIA time frame | During | No prep work required as have a taping team coming in prior to painting. Teaching staff/custodial staff/project manager will have everything ready--plug and play, well paint. | No |  | No |  | 700 |  |  | NONE |  | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 5
P. J. Jacobs Junior High | 1 | 5 | Paint front wall in 311 Contact person is Kelly Jung *****This project needs to be combined and added with project 3 and 9******** | Painting a classroom. There is not prep work with this project. Volunteers will just need to show up and paint. | This room will be taped on the Friday before SIA. The classroom will be prepped, paint delivered and all materials will be in the classroom. Volunteers should wear light clothes if warm as the air conditioning will not be on. All classroom materials will be down and furniture out of the way. Kelly Jung will provide a classroom map so volunteers can move the items in the room back for class Monday morning. Please bring ladders |  | 0 | No | Approved |  | General | PJ Jacobs JHS | 168 total feet to paint | SEE PROJECT #3:$ | 0 | Paint will be purchased by the district and delivered prior to SIA Sunday. PJs will use Sand dollar. | 0 | 0 | **Combine with project 3 and 9*** use project 3's info | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
P. J. Jacobs Junior High | 1 | 6 | Paint Cafeteria Contact person is Kelly Jung 715 572 8293 | You will be part of large team of people painting the cafeteria at PJ Jacobs | This room will be taped on the Friday before SIA. The cafeteria will be prepped, paint delivered and all materials will be in the classroom. Volunteers should wear light clothes if warm as the air conditioning will not be on. All surfaces clean and furniture out of the way. Please bring ladders. |  | 0 | No | Approved |  | Painting | cafeteria | 1760 total feet to paint | Paint brushes 2 pack 6x9.00:$54, Roller frames standard 6x5.00:$30, Paint Roller brushes standard 6x5.00:$30, Roller Frames 4 inches 4x3.99:$16, Paint Rollers 4 inch 4x3.99:$16, Paint Trays 4x2.99:$12, Paint Cups 8x1.99:$16, Paint 6x60:$360, This feature does not work------------>:$ | 445.56 | Paint will be purchased by the district and delivered prior to SIA Sunday. PJs will use Sand dollar. | 1 | 20 | within the allotted time | During | No prep work required as have a taping team coming in prior to painting. Teaching staff/custodial staff/project manager will have everything ready--plug and play. | No |  | No |  | 1760 total feet to paint | 6 |  | NONE |  | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 16
P. J. Jacobs Junior High | 1 | 7 | Paint hallway going to locker rooms **********Project is cancelled*************** |  |  |  | 0 | No | Cancelled |  | General | hallway going to locker rooms |  |  | 0 |  | 0 | 0 |  | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
P. J. Jacobs Junior High | 1 | 8 | Paint hallway by basement elevator ***PROJECT IS CANCELLED***** |  |  |  | 0 | No | Approved |  | General | basement elevator hallway |  |  | 0 |  | 0 | 0 |  | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
P. J. Jacobs Junior High | 1 | 9 | Paint front wall in 309 Contact person is Kelly Jung 715 572 8293 | Painting a classroom. All materials will be in the room and walls will be ready to paint. | This room will be taped on the Friday before SIA. The classroom will be prepped, paint delivered and all materials will be in the classroom. Volunteers should wear light clothes if warm as the air conditioning will not be on. All classroom materials will be down and furniture out of the way. Kelly Jung will provide a classroom map so volunteers can move the items in the room back for class Monday morning. Please bring ladders. |  | 0 | No | Approved |  | Painting | room 309 | 270 total feet | See project 3 as this is being combined with 3 and 5:$ | 0 | The paint is already ordered. This is a 3 room project with project 3 and 5 and it needs to be combined. Project 3 lists all the details. | 0 | 0 | within SIA time frame | During | No prep work required as have a taping team coming in prior to painting. Teaching staff/custodial staff/project manager will have everything ready--plug and play, well paint. | No |  | No |  | 270 |  |  | NONE |  | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
P. J. Jacobs Junior High | 1 | 10 | Taping rooms for painting Contact is Kelly Jung 715 572 8293 | You will be taping rooms to get them ready to be painted. This is a Friday night project starting as early as 4 p.m. | There is a substantial amount of feet that will need to be taped in order to start painting right away during SIA. |  | 0 | No | Pending |  | General | Room 314, 002, 217, 311, 309, and the cafeteria | N/A. | 25 rolls of 60 yard Painter's Tape 25x 4.99:$, 430 feet of painter's cloth I assume we have drop cloths?:$, This feature did not work ------------------------------>:$ | 125 | I will pick up painter's cloths and painters tape on the Wed before SIA. This will allow me to have everything set up for the taping crew that will come in on Friday night. I assume that we have painter's cloths in storage? Otherwise we will need to purchase some and not sure what that looks like. Tappers will need to tape everything exposed to possible paint contact, especially technology, trim, etc. Teaching staff with have all Smartboards covered. | 1 | 20 | Time will be based on the amount of volunteers that we have. It is hoped to take less than a couple hours. It will be next to impossible without a large crew of volunteers. | During | No prep work required. | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 20
Plover-Whiting Elementary | 1 | 1 | Wood bins for equipment in PE equipment room and bins for PE shoes that students borrow to be more neat and organized (similar to one in school for lost and found minus the clothes rack. PE equipment room Nancy Schuster |  |  | Unknown | 0 | No | Approved |  | General | Gym/PE Equipment Room | 92"L X 12" W X 76 3/4" H | Wood:$, Screws:$ | 0 | No permit needed. | 1 | 3 |  | Before | CompletepPrior to Spring into Action and install on the day of. | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 3
Plover-Whiting Elementary | 1 | 2 | Help pack library materials for moving library into storage. The library will be remodeled during the summer and everything needs to be packed up. 142 Library Rose Helm |  |  | School | 0 | No | Cancelled |  | General |  |  |  | 0 |  | 0 | 0 |  | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
Plover-Whiting Elementary | 1 | 4 | 4 literacy carts to help with organization of materials for flexible seating. room 123 at Plover-Whiting elementary Carrie Portzen | Woodworking: Build 4 library carts. | To be completed before Spring into Action. | Unknown | 0 | Yes | Approved |  | General | Room 123 | 23 1/4 " W X 14 1/2 D X 31 1/4" H | Wood:$, Wheels:$, Screws:$ | 0 |  | 0 | 0 |  | Before | The carts will need to be constructed before the day of Spring into Action. | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
Plover-Whiting Elementary | 1 | 5 | Games painted on playground to give kids more options at recess. Playground Macy Schmidt |  | *** Get re-checked by Don Keck. Any regular parking lot striping paint can be used. Sherwin Williams or any paint store would have the product. Check and make sure this should be done. Paint cannot be permanent. | Unknown | 0 | Yes | Approved |  | General | Playground |  |  | 0 |  | 0 | 0 |  | During | Find and buy stencils. Find paint that is non-permanent. | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
Point of Discovery School | 1 | 1 | We would like to request a sign for our school forest and ropes course. The sign will be placed near the low ropes course. Dan Lathrop |  | Check and make sure this should be done | Unknown | 0 | Yes | Approved |  | General |  |  |  | 0 |  | 0 | 0 |  | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
Roosevelt Elementary School | 1 | 1 | 6 Raised Garden Beds |  | Original Project Request: 6 Raised Garden Beds, Smartboard Steps in the Primary classrooms, coat/mitten racks for the primary classrooms, Gaga ball pit (2nd one) Playground and Primary Classrooms Kelly Snyder-Chase | PTO | 0 | No | Approved |  | General |  |  |  | 0 |  | 0 | 0 |  | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
Roosevelt Elementary School | 1 | 2 | Smartboard Steps in the Primary classrooms Kelly Snyder-Chase |  |  |  | 0 | No | Approved |  | General |  |  |  | 0 |  | 0 | 0 |  | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
Roosevelt Elementary School | 1 | 3 | Coat/mitten racks for the primary classrooms |  |  |  | 0 | No | Approved |  | General |  |  |  | 0 |  | 0 | 0 |  | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
Roosevelt Elementary School | 1 | 4 | Gaga ball pit (2nd one) |  |  |  | 0 | No | Approved |  | General |  |  |  | 0 |  | 0 | 0 |  | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
Stevens Point Area Senior High | 1 | 1 | Painting selected famous quotes from History and other social studies disciplines in the hallway between room 2236 and room 2356. Deb Kluz Baker |  | Before Separation: Painting selected famous quotes from History and other social studies disciplines in the hallway between room 2236 and room 2356. Hallway between room 2236 and room 2356 Deb Kluz Baker | Unknown | 0 | No | Approved |  | General |  |  |  | 0 | must get quotes approved first | 0 | 0 |  | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
Stevens Point Area Senior High | 1 | 2 | Painting selected famous quotes from History and other social studies disciplines in the hallway between room 2236 and room 2356 Deb Kluz Baker |  |  |  | 0 | No | Approved |  | General |  |  |  | 0 | must get quotes approved. | 0 | 0 |  | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
Washington Elementary School | 1 | 2 | bench with storage cubes like the picture uploaded but looking to have cubes instead of slots I can store books as a classroom library for access to students more like (2) 4 feetX 2 Feet wide storage units to put next to each other and then have a soft top (outdoor carpet so they can't pick at or not carpet) for students to sit or use to do work on. 110 side door next to receiving door first room to the left Dana Nelson | Bookcase bench for under smart board. 2 - 24 h x 48 L x 18 d bumped together. |  | Unknown | 0 | Yes | Approved |  | Furniture Making / Woodworking | Rm 110 | 24 h x 48 L x 18 d | 3 sheets 3/4" x 4' 8' Oak veneer plywood (menards):$180.00, 33 ft oak veneer edgebanding (menards):$13.00, Finish - Lacquer:$20.00, Outdoor carpeting 50 cents sq/ft ( Lowes):$10.00 | 223 | See rough sketch below. End panel should sit inside top and bottom since it will also be a bench. They would like outdoor carpeting on the top unlike what you see in the pic below. Shelves will be fixed. | 1 | 1 |  | Before |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 1
Washington Elementary School | 1 | 3 | Smart Board Steps 209 Angela Berger | Smart board steps | See special instructions below. | Unknown | 0 | No | Approved |  | Furniture Making / Woodworking | Rm 209 | See last year |  | 0 | Last year 3 special smart board steps were made for Washington. They would lik one more just like them. I understand there is a group that makes these and has all the dimensions and cost. It would be most accurate to go off of last years information. | 0 | 0 |  | Before |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
Washington Elementary School | 1 | 4 | Bookshelves for a classroom library and book boxes. The ones I have are starting to fall apart. 405 Jennifer Hintz | Bookcase 12in. d x 35in. h x 96in.L Oak veneer plywood |  | Unknown | 0 | Yes | Approved |  | Furniture Making / Woodworking | Rm 405 | 12in.d x 35in.h x 96in.L | 3 sheets 3/4" x 4' x 8' Oak veneer plywood (menards):$180.00, 47' oak veneer edgebanding (menards):$13.00, Finish - Lacquer:$20.00, Stain ( I have a quart from last year):$ | 213 | I have a special stain mixed to match the schools oak woodwork and is also on record at Sherwin Williams. Should have 2 dividers spaced equally with 2 adjustable shelves per cavity. Shelves should be adjustable. | 1 | 1 | 1 week | Before |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 1
Washington Elementary School | 1 | 5 | Paint some colorful activities on our new blacktop for kids to do at recess. This could help kids who are wandering around with no one to play with or provide additional choices for kids, especially when it's colder and they don't have boots/snow pants to play in the snow. Attached pictures are some examples of what I mean, but there are so many cool choices when you search playground stencils, etc. Blacktop by playground All staff |  | Get more details on where the quotes will be located, as well as get quotes approved from school district. Also find out with maintenance if there OK with this if they have to touch up paint. | Unknown | 0 | Yes | Cancelled | Ryan Ourada | General |  |  |  | 0 | No permanent paint | 0 | 0 |  | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
Washington Elementary School | 1 | 6 | Paint the playground blacktop - activites like a map or mazes. Something to do on the blacktop. playground all |  |  | Unknown | 0 | No | Cancelled | Ryan Ourada | General |  |  |  | 0 |  | 0 | 0 |  | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
Washington Elementary School | 1 | 7 | A planter bed in the front of the school like something in the project linked here. The goal would be to have the planter bed or planter boxes ready so that during our Tiger Pride spring meetings (or during Art Class) each student could paint a rock to add to the planter as pictured in the project linked. https://www.scarymommy.com/only-one-you-sharon-elementary-painted-rocks-art-project/. It would be amazing if rocks and outdoor paint could also be donated for this project as well. In front of the school as agreed upon by Mr. Ourada and the buildings and grounds personnel Teresa Jessee or other Tiger Pride Leader |  |  | Unknown | 0 | No | Cancelled |  | General |  |  |  | 0 |  | 0 | 0 |  | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
Washington Elementary School | 1 | 8 | Padded Bench: I would like a padded bench for the hallway outside of my classroom. This will allow groups of students a comfortable place to sit and read together and work in cooperative groups together. Last year my classroom was by the school entrance and my students utilized the bench daily that your church group made and is sitting outside of the office. If possible, I would like the bench to be the same size as the one by the office. Outside room 304 Chrissy Hall |  |  | Unknown | 0 | Yes | Cancelled |  | General |  |  |  | 0 |  | 0 | 0 |  | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
Washington Elementary School | 1 | 9 | rooms 400 and 401 build base cabinets on the north walls in both rooms so we can install the top cabinets. 400 and 401 gary zdroik | 1 bookcase @ 15d x 33 1/2h x 96L and 2 @ 15d x 33 1/2h x 54L Oak veneer plywood on casters. | They would also like to have 3 upper cabinets they already have hung back up in Rm 401. These are Schulist's made cabinets. One of the ends needs to be finished with laminate because it used to bump a wall. This is something I can take care of and would need a extra person to help hang the cabinet. | Unknown | 0 | Yes | Approved |  | Furniture Making / Woodworking/Cabinetry | Rm 400 & 401 | 1 @ 15d x 33 1/2h x 96L and 2 @ 15d x 33 1/2h x 54L | 3 sheets 3/4" x 4' x 8' Oak veneer plywood (menards) 3 shelves, 2 ends for 401:$180.00, 43' oak veneer edgebanding. Rm 400 (menards):$13.00, 8 - 2" swivel casters (menards) see pic below:$20.00, Finish - Lacquer Rm 400:$20.00, Stain - I have a quart of special mix for Washington:$, 3 sheets 3/4" x 4' x 8' Oak veneer plywood (menards) rm401:$180.00, 36' oak veneer edgebanding. Rm 401 (menards):$13.00, 12 - 2" swivel casters (menards) see pic below:$30.00, Finish - Lacquer Rm 401:$20.00, Stain - I have a quart of special mix for Washington:$ | 476 | Important: End panels must sit inside the top and bottom to properly support joint because of casters. 96L case should have 2 dividers spaced equally with 2 adjustable shelves per cavity (6 shelves per unit). 54L cases will bump together to equal 108L with 1 divider each and 2 adjustable shelves per cavity. I have a special stain for Washington that matches it's oak woodwork. | 1 | 1 | 2 weeks | Before |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 1
Washington Elementary School | 1 | 10 | build a shelving unit for the phyed teacher on the stage behind the back curtain. the stage in the gym. will have to think of a good idea. ben or gary | Garage/Basement type rough shelving 2x4 construction with osb board for shelving. 24d x 16ftL x 84h | They would like these painted. School would supply paint per Gary Zdroik. 2 units 24h x 16ft L x 84h put together to equal 16ft L. Would be easiest to paint the parts ahead of SIA day. They would also like them secured to the wall in case kids would try and climb on them. | Unknown | 0 | Yes | Approved |  | General Carpentry/General | Stage in gymnasium behind the curtain | 24d x 16ft L x 84h | 21 - 2x4x8 framing studs:$63.00, 3 sheets 7/16" x 4' x 8' OSB board:$27.00 | 90 | Shelving should run from fire extinguisher on right side to the left leaving room for a metal cage they have for storing game balls. 2 shelves plus top. They also have 3 volleyball posts that they would like to stand up. I thought we could make something simple on the end of the shelving to lock them in a stand up position. See pic of them below. | 1 | 2 | 1 week | Before | Could cut materials ahead of time and make the shelf box and assemble on sight. Depends how a person wants to make it. Be easier to paint ahead when in pieces. See rough sketch below. | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 2
Washington Elementary School | 1 | 11 | Padded Bench: I would like a padded bench for the hallway outside of my classroom...something similar to the bench outside of the main office (blue seat covering preferred over yellow). This will allow groups of students a comfortable place to read and work in cooperative groups. Bench would be placed outside of room #302 Kim Shuda |  | Here are some additional notes. | Unknown | 0 | No | Cancelled |  | General |  |  |  | 0 |  | 0 | 0 |  | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
Washington Elementary School | 1 | 12 | Request #1: Create a shelf unit that will fit inside a large music closet in the music room. This shelving unit will be used for the general music room props that need to be stacked properly or they will become crushed. The other shelving unit is for the band teacher to keep large and small instruments safe instead of stacking everything in one closet. Request #2: A wooden box (20' long X 8 1/2" tall, needs to be constructed for a Washington student, to stand on in order to get on a classroom chair in the music room. This student is very small/short and needs assistance getting onto a regular chair during class.This box would enable the student to properly sit in the chair with no assistance. Request #3: One door panel on the large closet doors that were varnished last spring, was dented during the renovation (looks like a ladder was used). A dent was created and needs to be sanded down and revarnished. Room 216 Mrs. Sandy Weyers | Cut 4 shelves for closet and mount adjustable metal tracks for them to sit on | The other 2 projects I will take care of. I have some extra materials I can make a box step out of. They are renovating her room next summer so we will wait to fix the door just in case the do more damage. | School | 0 | Yes | Approved |  | Furniture Making / Woodworking/Cabinetry | Rm 216 |  | 1 sheet 3/4" x 4' x 8' plywood (menards):$35.00, 8 @ 60" metal shelf tracks. See pic below 2.39 ea. (menards):$20.00, 2 pks. shelf clips. See pic below 2.69 ea. (menards):$6.00 | 61 | Cabinet is about 77 inches high. Mount metal tracks with equal gap top and bottom. Put them 4 inches off the back and front. 2 shelves per cabinet. Shelves are 19 3/8 wide x 38 5/8 deep. Whatever the profile of the track is will need to be subtracted from the width. The tracks will be surfaced mounted. Cut the shelves ahead of SIA day. Going from the left the shelves go in door #6 and #9. | 1 | 1 | 1 day | Before |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 1
Washington Elementary School | 1 | 13 | Large cabinets along the north wall of our classrooms. We would like tall cabinets with doors in one room and a base cabinet with doors and a counter top in the other. The tall cabinet space is 9 feet wide and 7-9 feet tall. The base cabinet area is 100 inches long with wall cabinets that same length already hanging above that open space. Our special education classroom contains many academic and sensory materials in a variety of shapes and sizes. Large cabinets allow us to store oddly shaped items out of reach when not in use. The ability to close and secure the doors also keeps materials out of reach when safety concerns arise.. 400/401 Bridget Wilson |  |  | Unknown | 0 | No | Cancelled | Ryan Ourada | General |  |  |  | 0 |  | 0 | 0 |  | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
Washington Elementary School | 1 | 14 | I would like new bookshelves to hold my collection of books for my classroom library and my students' book boxes. Similar to the attached picture. Room 406 Traci Freund | Bookcase 40in. h x 96in. L x 15in. d Oak veneer plwood on casters. |  | School | 0 | Yes | Approved |  | Furniture Making / Woodworking | Rm 406 | 40 h x 96 L x 15 d. | 3 sheets @ 3/4" x 4' x 8' Oak veneer plywood (menards):$180.00, 50ft Oak veneer edgebanding (menards):$13.00, 8 - 2" swivel casters (menards) see pic below:$20.00, Stain - I have a quart of special mix for Washington:$, Finish - lacquer:$20.00, material 6:$, material extra 1:$, material extra 2:$ | 213 | Important: End panels need to sit between top and bottom to properly support weight on casters. 2 divider panels spaced equally with 2 adjustable shelves in each cavity. | 1 | 1 | 1 week | Before |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 1
Washington Elementary School | 1 | 15 | A moveable door to separate the cubbie room fro the bathroom area. 408 Cheryl Behnke |  | Here are some additional notes. | Unknown | 0 | No | Cancelled |  | General |  |  |  | 0 |  | 0 | 0 |  | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
Washington Elementary School | 1 | 16 | I would like countertop to be added to the left side of the vent to the corner, below the window sill, 408 Swiontek/Behnke | Make 2 bookcases 32 h x 60 L x 15 d Oak veneer plywood on casters |  | Unknown | 0 | Yes | Approved |  | Furniture Making / Woodworking | Rm 408 | 32 h x 60 L x 15 d | 4 sheets 3/4" 4' x 8' oak veneer plywood:$180.00, 60 ft Oak veneer edgebanding (menards):$19.00, 12 - 2" swivel casters - see pic below (menards):$30.00, Finish - Lacquer:$20.00 | 249 | Important: End panels must sit inside top and bottom to properly support joint because of casters. 1 divider per bookcase with 2 adjustable shelves in each cavity. | 1 | 1 | 1 week | Before |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 1
Washington Elementary School | 1 | 17 | paint the boiler room boiler room garyzdroik |  | Here are some additional notes. | Unknown | 0 | No | Cancelled | Ryan Ourada - A custodian was already painting it when we checked it out. | General |  |  |  | 0 |  | 0 | 0 |  | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
Washington Elementary School | 1 | 18 | build a heavy duty shelf in room 411 in the back of the room to store chairs on top. 411 gary zdroik | Rough 2 x 4 shelving for utility room. Painted | They would like these painted like project 10. School would supply paint. 2 sections @ 24d x 8ft L x 84h for the west wall. 1 section 24d x 78L x 84h for the south wall. The wall if you look at the ceiling pic below shows that it's at an angle. We could make units to bump together at 90 degrees or just bump them against the walls and let them be at an angle. See rough sketch pic below. | Unknown | 0 | Yes | Approved |  | General Carpentry | Rm 411 |  | 29 - 2 x 4 x 8 framing studs:$87.00, 5 sheets @ 7/16 x 4 x 8 OSB board for shelving:$45.00 | 132 |  | 0 | 0 |  | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
Washington Elementary School | 1 | 19 | Paint the outside tiles that are attached to building underneath the windows. Outside Ryan Ourada |  | Here are some additional notes. | Unknown | 0 | No | Cancelled |  | General |  |  |  | 0 |  | 0 | 0 |  | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
Washington Elementary School | 1 | 20 | Build a slotted bookshelf to hold big books. 208 Courtney Thomas |  | Here are some additional notes. | Unknown | 0 | No | Cancelled | Ryan Ourada | General |  |  |  | 0 |  | 0 | 0 |  | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
Washington Elementary School | 1 | 21 | My room tiny but if possible, I would like cabinets along the top 3 walls that are open so that I can store different academic curriculum resources and other subject area manipulatives. The other thing I would like to have is a bookshelf behind the door to store different reading leveled books. 416- install a bookshelf next to the teacher desk behind the door Chao Lao |  | Here are some additional notes. | Unknown | 0 | No | Cancelled | Ryan Ourada | General |  |  |  | 0 |  | 0 | 0 |  | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0
Washington Elementary School | 1 | 22 | A shelf unit for the speech and language room to hold my books and supplies that are still being housed in a storage area because my room has limited shelving/storage. 413 Amy A Zdroik |  | Here are some additional notes. | Unknown | 0 | No | Cancelled | Ryan Ourada | General |  |  |  | 0 |  | 0 | 0 |  | During |  | No |  | No | [6 empty] | No | 0 | No | No |  |  | No | Not Ready | No | No | No | No | Needs to be submitted | No |  | No | 0

## Project Mgr & Site Coor
Spring Into Action 2020
Project Manager & Site Coordinator
Monday, February 17, 2020
SiteName | Role | LastName | FirstName | MobilePhoneNumber | HomePhoneNumber | Email
Bannach Elementary School | Site Coordinator | Sowiak | Stacey |  |  | ssowiak@msn.com
Ben Franklin Junior High | Project Manager | Nicholson | Mike | 715-570-2737 | 715-341-5708 | nichkath@hotmail.com
Boston School Forest | Project Manager | Sankey | Dale | 715-347-2201 | 715-345-1806 | dalesankey1@gmail.com
Jefferson Elementary School | Project Manager | johnson | bradley | (715) 347-0560 | 715-343-8906 | rangerbrad1969@gmail.com
Kennedy Elementary School | Project Manager | Gaboda | Tony | (715) 340-9580 |  | studbros.tg@gmail.com
Madison Elementary School | Project Manager | Hansen | David | 715-340-2544 | 715-342-5801 | dhansen@woodlandschurch.org
McDill Elementary School | Project Manager | Erickson | Brian |  |  | brerickson123@gmail.com
McKinley Center Elementary | Project Manager | Blakey | William | 715-218-7815 | 715-570-6865 | willblky@aol.com
Plover-Whiting Elementary | Project Manager | Merrill | Tim | (715) 345-1751 | 715-345-1751 | 4cheeseheads@charter.net
Roosevelt Elementary School | Project Manager | Groshek | Nate | 715-370-2583 |  | nategroshek88@gmail.com
Stevens Point Area Senior High | Project Manager | Dubos | Jenny | (630) 310-0327 |  | dubosemail@yahoo.com
Bannach Elementary School | Project Manager | Edwards | Trey |  |  | treyedwards0559@gmail.com
Ben Franklin Junior High | Project Manager | Nicholson | Mike | 715-570-2737 | 715-341-5708 | nichkath@hotmail.com
Kennedy Elementary School | Project Manager | Gaboda | Tony | (715) 340-9580 |  | studbros.tg@gmail.com
Madison Elementary School | Project Manager | Hansen | David | 715-340-2544 | 715-342-5801 | dhansen@woodlandschurch.org
Roosevelt Elementary School | Project Manager | Groshek | Nate | 715-370-2583 |  | nategroshek88@gmail.com
Stevens Point Area Senior High | Project Manager | Dubos | Jenny | (630) 310-0327 |  | dubosemail@yahoo.com
All Schools | Project Manager | Test | Test |  |  | spring_into_action@woodlandschurch.org
All Schools | Project Manager | Lynn | Bree |  |  | breelynnvan@gmail.com
Boston School Forest | Project Manager | Kazda | Jacob |  |  | jacobhenry99@hotmail.com
Jefferson Elementary School | Project Manager | johnson | bradley | (715) 347-0560 | 715-343-8906 | rangerbrad1969@gmail.com
Plover-Whiting Elementary | Project Manager | Merrill | Tim | (715) 345-1751 | 715-345-1751 | 4cheeseheads@charter.net
Kennedy Elementary School | Project Manager | Gaboda | Rebecca | (715) 340-9580 |  | rsager3@gmail.com
McDill Elementary School | Project Manager | Christianson | Jeff | (715) 540-0072 |  | christiansonjeff@yahoo.com
P. J. Jacobs Junior High | Project Manager | Jung | Kelly |  |  | kjung@pointschools.net
McKinley Center Elementary | Project Manager | McQuillen | Phil |  |  | phillip.mcquillen@sentry.com
Fernandez Center | Project Manager | Hayakawa | Howard | 715-204-0397 |  | howard.hayakawa@gmail.com
Washington Elementary School | Project Manager | Daniels | Mike |  |  | vinny@charter.net

## Team Leaders
Spring Into Action 2020
Team Leaders
Monday, February 17, 2020
SiteName | Role | LastName | FirstName | Email | MobilePhoneNumber | HomePhoneNumber | ProjectVolunteerRoleStatusLabel
Bannach Elementary School | Liaison | Hayakawa | David | david.hayakawa@gmail.com | (715) 305-4840 |  | Agreed
Bannach Elementary School | Team Leader | Hayakawa | David | david.hayakawa@gmail.com | (715) 305-4840 |  | Agreed
All Schools | Team Leader | Hayakawa | David | david.hayakawa@gmail.com | (715) 305-4840 |  | Agreed

## Volunteers
Spring Into Action 2020
Volunteers
Monday, February 17, 2020
Name | Contact-Phone | Site-Name | Proj-Num | Project-Description
Hayakawa, David | (715) 305-4840 | Bannach Elementary School | 1 | Clean-up grounds outside of Bannach
Hayakawa, David | (715) 305-4840 | All Schools | 2 | 4454